## Initial
Project Plan: INTERACTIVE MEDIA RESEARCH
Phase | Activity | Estimated Time (hrs) | Due Date | Actual Time (hrs) | Actual Date | Variance (hrs)
Planning | Ask people if they want to be my client | 1 | 2021-08-06 | 2 | 2021-07-31 | 1
| Work through possible project ideas | 1 | 2021-08-06 | 2 | 2021-07-31 | 1
| Narrow down to one idea | 0.5 | 2021-08-06 | 1 | 2021-08-04 | 0.5
| Decide what I could make the idea in | 0.5 | 2021-08-06 | 0.5 | 2021-08-05 | 0
| created the problem statement | 0.5 | 2021-08-06 | 0.5 | 2021-08-05 | 0
| Prototype layout | 2 | 2021-08-06 | 2 | 2021-08-05 | 0
Defining | Research text media | 2 | 2021-08-13 | 1 | 2021-08-10 | -1
| Test text media | 1 | 2021-08-13 | 1 | 2021-08-10 | 0
| Text media write up | 3 | 2021-08-13 | 3 | 2021-08-10 | 0
| Research audio media | 1 | 2021-08-20 | 1 | 2021-08-18 | 0
| Test audio media | 1 | 2021-08-20 | 2 | 2021-08-18 | 1
| Audio media write up | 2 | 2021-08-20 | 2.5 | 2021-08-19 | 0.5
| Research image media | 2 | 2021-08-27 | 2 | 2021-08-25 | 0
| Test image media | 1 | 2021-08-27 | 1.5 | 2021-08-25 | 0.5
| Image media write up | 2 | 2021-08-27 | 2 | 2021-08-26 | 0
| Research video media | 2 | 2021-09-03 | 1 | 2021-09-01 | -1
| Test video media | 1 | 2021-09-03 | 2 | 2021-09-01 | 1
| Video media write up | 2 | 2021-09-03 | 2 | 2021-09-02 | 0
| Research Prototyping | 2 | 2021-09-10 | 1 | 2021-09-04 | -1
| Test Prototyping | 2 | 2021-09-10 | 1 | 2021-09-04 | -1
| Prototyping write up | 2 | 2021-09-10 | 1.5 | 2021-09-04 | -0.5
| Research testing | 2 | 2021-09-10 | 1 | 2021-09-08 | -1
| Create testing doc | 1 | 2021-09-10 | 1.5 | 2021-09-08 | 0.5
| Testing write up | 2 | 2021-09-10 | 2 | 2021-09-11 | 1
Creating | Prototype system functionality | 1 | 2021-09-17
| Prototype system layout | 1 | 2021-09-17
| Test prototypes on uses | 3 | 2021-09-22
| Build basic layout | 2 | 2021-09-24
| Add buttons | 1 | 2021-09-24
| Create gifs | 2 | 2021-09-26
| Add gifs to form and get them to run on click | 2 | 2021-09-27
| Create random number generator and win/loss states | 2 | 2021-09-27
| Create counters for throw, guesses wins and loses | 2 | 2021-09-28
| Add music | 2 | 2021-09-28
| Add sound effects | 2 | 2021-09-29
| Create video tutroial | 1 | 2021-09-29
| Add video | 3 | 2021-09-30
| Create unit tests | 1 | 2021-09-30
| Make sure everthing is working correctly | 1 | 2021-10-01
| Finish off app | 1 | 2021-10-01
Testing | Test prototypes on uses | 3 | 2021-09-22
| App functionality testing | 3 | 2/10/021
| App useabilty testing | 3 | 4/10/021
| Make changes to app | 2 | 5/10/022
Implementation | Create final release app exc file | 1 | 8/10/022
| Client training and review | 1 | 9/10/023
|  | Total Estimated hours |  | Total Actual hours |  | Total Variance
|  | 76.5 |  | 37 |  | 1.5

## Final
Project Plan: INTERACTIVE MEDIA RESEARCH
Phase | Activity | Estimated Time (hrs) | Due Date | Actual Time (hrs) | Actual Date | Variance (hrs)
Planning | Ask people if they want to be my client | 1 | 2021-08-06 | 2 | 2021-07-31 | 1
| Work through possible project ideas | 1 | 2021-08-06 | 2 | 2021-07-31 | 1
| Narrow down to one idea | 0.5 | 2021-08-06 | 1 | 2021-08-04 | 0.5
| Decide what I could make the idea in | 0.5 | 2021-08-06 | 0.5 | 2021-08-05 | 0
| created the problem statement | 0.5 | 2021-08-06 | 0.5 | 2021-08-05 | 0
| Prototype layout | 2 | 2021-08-06 | 2 | 2021-08-05 | 0
Defining | Research text media | 2 | 2021-08-13 | 1 | 2021-08-10 | -1
| Test text media | 1 | 2021-08-13 | 1 | 2021-08-10 | 0
| Text media write up | 3 | 2021-08-13 | 3 | 2021-08-10 | 0
| Research audio media | 1 | 2021-08-20 | 1 | 2021-08-18 | 0
| Test audio media | 1 | 2021-08-20 | 2 | 2021-08-18 | 1
| Audio media write up | 2 | 2021-08-20 | 2.5 | 2021-08-19 | 0.5
| Research image media | 2 | 2021-08-27 | 2 | 2021-08-25 | 0
| Test image media | 1 | 2021-08-27 | 1.5 | 2021-08-25 | 0.5
| Image media write up | 2 | 2021-08-27 | 2 | 2021-08-26 | 0
| Research video media | 2 | 2021-09-03 | 1 | 2021-09-01 | -1
| Test video media | 1 | 2021-09-03 | 2 | 2021-09-01 | 1
| Video media write up | 2 | 2021-09-03 | 2 | 2021-09-02 | 0
| Research Prototyping | 2 | 2021-09-10 | 1 | 2021-09-04 | -1
| Test Prototyping | 2 | 2021-09-10 | 1 | 2021-09-04 | -1
| Prototyping write up | 2 | 2021-09-10 | 1.5 | 2021-09-04 | -0.5
| Research testing | 2 | 2021-09-10 | 1 | 2021-09-08 | -1
| Create testing doc | 1 | 2021-09-10 | 1.5 | 2021-09-08 | 0.5
| Testing write up | 2 | 2021-09-10 | 2 | 2021-09-11 | 1
Creating | Prototype system functionality | 1 | 2021-09-17 | 3 | 2021-09-17 | 2
| Prototype system layout | 1 | 2021-09-17 | 1 | 2021-09-18 | 0
| Test prototypes on uses | 3 | 2021-09-22 | 3 | 2021-09-22 | 2
| Build basic layout | 2 | 2021-09-24 | 2 | 2021-09-24 | 0
| Add buttons | 1 | 2021-09-24 | 1 | 2021-09-24 | 0
| Create gifs | 2 | 2021-09-26 | 3 | 2021-09-25 | 1
| Add gifs to form and get them to run on click | 2 | 2021-09-27 | 1 | 2021-09-26 | -1
| Create random number generator and win/loss states | 2 | 2021-09-27 | 1 | 2021-09-26 | -1
| Create counters for throw, guesses wins and loses | 2 | 2021-09-28 | 3 | 2021-09-29 | 1
| Add music | 2 | 2021-09-28 | 2 | 2021-09-29 | 0
| Add sound effects | 2 | 2021-09-29 | 1 | 2021-09-30 | -1
| Create video tutroial | 1 | 2021-09-29 | 0.5 | 2021-09-30 | -0.5
| Add video | 3 | 2021-09-30 | 2 | 2021-10-01 | -1
| Create unit tests | 1 | 2021-09-30 | 2 | 2021-10-01 | 1
| Make sure everthing is working correctly | 1 | 2021-10-01 | 1 | 2021-10-02 | 0
| Finish off app | 1 | 2021-10-01 | 1 | 2021-10-02 | 0
Testing | Test prototypes on uses | 3 | 2021-09-22 | 3 | 2021-09-22 | 2
| App functionality testing | 3 | 2/10/021 | 3 | 2021-10-02 | 1
| App useabilty testing | 3 | 4/10/021 | 4 | 2021-10-03 | 1
| Make changes to app | 2 | 5/10/022 | 3 | 2021-10-05 | 1
Implementation | Create final release app exc file | 1 | 8/10/022 | 1 | 2021-10-06 | 0
| Client training and review | 1 | 9/10/023 | 3 | 10/10/023 | 2
|  | Total Estimated hours |  | Total Actual hours |  | Total Variance
|  | 76.5 |  | 81.5 |  | 11